## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | olx.ba (responsive)
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 06. 01. 2026. | Benjamin Muratović | Funkcionalnost pretrage i filtriranja ne vrši validaciju raspona cijene kada je minimalna cijena veća od maksimalne. Sistem prikazuje poruku "Nema rezultata", umjesto da upozori korisnika na neispravan unos, što može dovesti do konfuzije. Link za showcase: https://edufit-my.sharepoint.com/:v:/g/personal/benjamin_muratovic_edu_fit_ba/IQDAELXUqnNaSoaWvqyFO-NaAdo4xLmpLhtCdddijx4RNr4?e=bqj0x5 | Executing/Controlling | Testing | Medium | Development Team | 06. 01. 2026. | 2h | New | Implementirati validaciju unosa na klijentskoj strani kako bi se spriječio unos minimalne cijene veće od maksimalne. |  |  | Nedostaje validacija | New
2 | 06. 01. 2026. | Benjamin Muratović | Funkcionalnost pretrage dozvoljava unos specijalnih karaktera (npr. %&%) bez ikakve validacije. Sistem prikazuje poruku "Nema rezultata" umjesto da obavijesti korisnika da je unos neispravan, što ovodi do nejasnog ponašanja sistema. Link za showcase: https://edufit-my.sharepoint.com/:v:/g/personal/benjamin_muratovic_edu_fit_ba/IQCpLaDK-IWxRYFMy8sVSp7bAW-VazjE8EvErw3_4ITW88Q?e=7vPaax | Executing/Controlling | Testing | Medium | Development Team | 06. 01. 2026. | 2h | New | Ograničiti ili validirati unos u polju za pretrage te prikazati jasnu poruku korisniku u slučaju neispravnih znakova |  |  | Nedostaje validacija | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 06. 01. 2026. | Benjamin Muratović | Funkcionalnost pretrage ne nudi prijedlog ili alternativne rezultate kada korisnik napravi manju tipografsku grešku u pojmu za pretragu (npr. „iphne“ umjesto „iphone“), već odmah prikazuje poruku „Nema rezultata“, što negativno utiče na korisničko iskustvo. Link za showcase: https://edufit-my.sharepoint.com/:v:/g/personal/benjamin_muratovic_edu_fit_ba/IQCvonx9eof6Q4yXn84lDV-hAZ5-R_48YEnO8L3qhoVjquY?e=FAaYvB | Executing/Controlling | Testing | Low | Development Team | 06. 01. 2026. | 3h | New | Implementirati mehanizam za prepoznavanje tipografskih grešaka i ponuditi prijedloge za ispravku ili slične rezultate (npr. “Da li ste mislili…?”). |  |  | Nedostaje validacija | In Progress | Medium | Initiating | Concept
4 | 06. 01. 2026. | Selma Alagić | Funkcionalnost filtriranja proizvoda prema unesenoj cijeni (od/do) se ne izvršava ispravno u slučaju kada unesemo da je cijena od: 0 i do: 0. Ukoliko odaberemo bilo koju kategoriju i filtriramo proizvode prema cijeni na taj način, sistem ni na koji način ne obavještava korisnike da proizvod u tom opsegu cijene i odabranoj kategoriji ne postoji već prikaže proizvode odabrane kategorije sa nasumičnim cijenama koje ne odgovaraju zadanom filteru. Link za showcase: https://edufit-my.sharepoint.com/:v:/g/personal/alagic_selma_edu_fit_ba/IQA99-mhH8N3QIWCzYJ7a_TXASjWGLenJ4i4WkfZAaxz6Rc?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=nEUFsN | Executing/Controlling | Testing | High | Development Team | 06. 01. 2026. | 4h | New | Ograničiti ili validirati unos cijene i prikazati korisniku jasnu poruku ako unesena vrijednost nije ispravna, a ako je raspon cijene validan, prikazati relevantne rezultate za taj filter. |  |  | Logička greška, nedostaje validacija | Completed | Low | Planning | Requirements
5 | 06. 01. 2026. | Selma Alagić | Funkcionalnost resetovanja svih filtera (tj. opcija “Clear All”) trenutno nije dostupna. Kada korisnici odaberu više filtera (npr. cijena, lokacija, proizvođač), moraju ih uklanjati jedan po jedan, iako bi možda željeli ukloniti sve odjednom i odabrati nove vrijednosti ili početi novu pretragu. Ovo nije optimalno korisničko iskustvo jer povećava broj klikova, usporava pretragu i može biti frustrirajuće, posebno ako korisnik želi brzo promijeniti kriterije pretrage. Link za showcase: https://edufit-my.sharepoint.com/:v:/g/personal/alagic_selma_edu_fit_ba/IQCoCCvWqQIoTosPBN6pwZS8Af_wX0ANCYYx8qFbx1_Y3fU?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=kznKW3 | Executing/Controlling | Testing | High | Development Team | 06. 01. 2026. | 1d | New | Dodati opciju “Clear All” koja će biti jasno vidljiva korisnicima i omogućiti uklanjanje svih filtera odjednom, čime će se poboljšava efikasnost pretrage i zadovoljstvo korisnika. |  |  | Nedostaje funkcionalnost |  |  | Executing/Controlling | Design
6 | 06. 01. 2026. | Selma Alagić | Polje za unos ključnih riječi kod pretrage proizvoda nema ograničenje unosa karaktera. Ako korisnik unosi ogroman broj karaktera (npr. 270), sistem korisnicima prikazuje poruku ‘nema rezultata’ bez bilo kakvog upozorenja da je unos izvan opsega. Unesena ključna riječ se šalje na backend te se bezpotrebno vrši pretraživanje baze iako se mogla validacija prikazati na frontendu bez slanja zahtjeva na backend. Link za showcase: https://edufit-my.sharepoint.com/:v:/g/personal/alagic_selma_edu_fit_ba/IQCV2j3WZyJ0TqaAUo2t-ctRAfyvKNIv2n74mKO0H18zF0c?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=h5eted | Executing/Controlling | Testing | High | Development Team | 06. 01. 2026. | 2h | New | Prikazati korisniku upozorenje ili validacijsku poruku ukoliko pokuša unijeti više od dozvoljenog broja karaktera. |  |  | Nedostaje validacija |  |  | Closing | Development
7 | 06. 01. 2026. | Selma Alagić | Kada korisnik pretražuje proizvod koji ne postoji i ne koristi nikakve filtere, opcija ‘Očisti filtere’ se pojavljuje tek kada nema rezultata za pretragu. Ovo može zbuniti korisnika jer nije primijenio nikakve filtere, a opcija za njihovo uklanjanje se bespotrebno prikazuje. Link za showcase: https://edufit-my.sharepoint.com/:v:/g/personal/alagic_selma_edu_fit_ba/IQDlqIIQqC6aR66YgHYnmd2NAU6A3tKtVRcIual61Gam2zI?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=T7HmaH | Executing/Controlling | Testing | Medium | Development Team | 06. 01. 2026. | 2h | New | Opcija ‘Očisti filtere’ treba se prikazivati samo kada su filteri aktivni. Ako korisnik nije primijenio nijedan filter, opcija se ne prikazuje, čak ni kada nema rezultata pretrage. |  |  | Pogrešna UI logika |  |  |  | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).